## Sheet1
Overall Status	YELLOW			Total Risk	0.430808080808081

	Description	Votes
Metric	The total number of defects			Low score	1.33333333333333
Minimal Risk	The number of defects are well below where expected	3		Med score	5.33333333333333
Low Risk	The number of defects are about where we expect	4		High Score	9
Reasonable Risk	The number of defects are slightly above what is expected	8		Total votes	24
High Risk	The number of defects greatly exceed expectations	9		Risk	0.652777777777778

Assessed Risk		YELLOW

	Description	Votes
Metric	Schedule feasibility			Low score	2.66666666666667
Minimal Risk	The project can be easily completed in the scheduled time	7		Med score	4.66666666666667
Low Risk	The project can be completed in the scheduled time with strict time management	8		High Score	2
Reasonable Risk	The project may be completed in the scheduled time, but will require crunch	7		Total votes	24
High Risk	The project is unlikely to be completed in the scheduled time	2		Risk	0.388888888888889

Assessed Risk		YELLOW

	Description	Votes
Metric	Design progress			Low score	2
Minimal Risk	The design is complete	11		Med score	4
Low Risk	The design is mostly complete and no major problems are noted	6		High Score	1
Reasonable Risk	The design is incomplete and one major problem is noted with strategies to mitigate	6		Total votes	24
High Risk	The design is incomplete, has several major problems with no plans to mitigate	1		Risk	0.291666666666667

Assessed Risk		GREEN

	Description	Votes
Metric	Implementation progress			Low score	2
Minimal Risk	The implementation is ahead of schedule	5		Med score	3.33333333333333
Low Risk	The implementation is on schedule	6		High Score	6
Reasonable Risk	The implementation is slightly behind schedule	5		Total votes	22
High Risk	The implementation is far behind schedule	6		Risk	0.515151515151515

Assessed Risk		YELLOW

	Description	Votes
Metric	Integration progress			Low score	2.66666666666667
Minimal Risk	No major integration problems have been detected	9		Med score	4.66666666666667
Low Risk	Minor integration problems have been detected	8		High Score	0
Reasonable Risk	At least one major integration problem has been detected, with plans to remedy	7		Total votes	24
High Risk	Multiple major integration problems have been detected, with no plans to rememdy	0		Risk	0.305555555555556

Assessed Risk		GREEN